## WBS & Gantt
Fabor OS Master Plan — WBS & Gantt
Programme plan · Phases 0–5 · 42 months · engineering, AI, compliance, go-to-market and funding
[5 empty] | Milestones ▶ |  |  | MS1 Launch | [5 empty] | MS2 Pilot |  |  |  |  | MS3 Leasing live | [5 empty] | MS4 Commercial | [9 empty] | MS5 Migration | [11 empty] | MS6 Global
WBS | Activity | Milestone | Start (month) | End (month) | Months | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42
1 | Phase 0 · Foundations
1.1 | Programme and company
1.1.1 | Founding team: architect, ledger lead, platform lead | MS1 | 1 | 2 | 2
1.1.2 | Seed funding close | MS1 | 1 | 3 | 3
1.1.3 | Name and logo trademark search and filing | MS1 | 1 | 3 | 3
1.1.4 | Design partner shortlist and LOIs | MS1 | 1 | 3 | 3
1.2 | Delivery platform
1.2.1 | Monorepo, Maven modules, CI with licence gate and SBOM | MS1 | 1 | 1 | 1
1.2.2 | Dev, SIT and performance environments | MS1 | 1 | 2 | 2
1.2.3 | Observability stack and runbook template | MS1 | 2 | 3 | 2
1.3 | Platform kernel and ledger
1.3.1 | Money, calendars, day counts, tenancy libraries | MS1 | 1 | 2 | 2
1.3.2 | Ledger domain on PostgreSQL with conformance suite | MS1 | 2 | 2 | 1
1.3.3 | Oracle LedgerStore, outbox, Debezium, Kafka | MS1 | 2 | 3 | 2
1.3.4 | Group commit, sharding, hot accounts | MS1 | 3 | 3 | 1
1.3.5 | Benchmark 10k/s and chaos tests | MS1 | 3 | 3 | 1
1.4 | Open source launch
1.4.1 | Agent gateway skeleton with read-only tools | MS1 | 3 | 3 | 1
1.4.2 | Public repository, docs, governance, benchmark report | MS1 | 3 | 3 | 1
2 | Phase 1 · Retail and virtual bank MVP
2.1 | Product engine
2.1.1 | Product DSL, CEL, schedule and interest engines | MS2 | 4 | 6 | 3
2.1.2 | Simulator and golden tests | MS2 | 5 | 7 | 3
2.1.3 | Master Builder and maker-checker publishing | MS2 | 6 | 8 | 3
2.1.4 | Partitioned time-wheel scheduler (ADR-0007) | MS2 | 4 | 6 | 3
2.2 | Banking services
2.2.1 | Party, KYC status, consents | MS2 | 4 | 5 | 2
2.2.2 | Deposits: savings, current, term, pockets, WHT | MS2 | 5 | 7 | 3
2.2.3 | Personal and nano loans | MS2 | 6 | 8 | 3
2.2.4 | GL mapping and daily reconciliation | MS2 | 6 | 8 | 3
2.3 | Integration and channels
2.3.1 | PromptPay and QR, eKYC, credit bureau | MS2 | 5 | 8 | 4
2.3.2 | Onboarding and origination workflows | MS2 | 6 | 8 | 3
2.3.3 | Back-office console v1 | MS2 | 6 | 9 | 4
2.3.4 | Reference mobile app | MS2 | 7 | 9 | 3
2.4 | AI
2.4.1 | Credit decisioning with reason codes | MS2 | 6 | 8 | 3
2.4.2 | Document intelligence | MS2 | 6 | 8 | 3
2.4.3 | Fraud scoring on posting path, sanctions screening | MS2 | 7 | 9 | 3
2.4.4 | Customer assistant (read and servicing requests) | MS2 | 7 | 9 | 3
2.5 | Scale, security and compliance
2.5.1 | Scale-out test 100k/s across 10 cells | MS2 | 8 | 9 | 2
2.5.2 | PII vault, PDPA consent, audit log | MS2 | 5 | 8 | 4
2.5.3 | Penetration test and IT risk assessment | MS2 | 8 | 9 | 2
2.5.4 | Regulator sandbox engagement | MS2 | 6 | 9 | 4
2.6 | Business
2.6.1 | Design partner contract signed | MS2 | 4 | 6 | 3
2.6.2 | Series A funding | MS2 | 7 | 9 | 3
2.6.3 | Staff pilot and 30 days of zero-difference reconciliation | MS2 | 9 | 9 | 1
3 | Phase 2 · Asset finance and leasing
3.1 | Hire purchase and leasing
3.1.1 | HP: annuity from flat, EIR, balloon, VAT, e-Tax invoices | MS3 | 10 | 12 | 3
3.1.2 | Finance and operating leases (TFRS 16) | MS3 | 11 | 13 | 3
3.1.3 | Asset register, title, insurance, dealer channel | MS3 | 10 | 12 | 3
3.1.4 | Early settlement rebates | MS3 | 12 | 13 | 2
3.2 | Fleet and floor plan
3.2.1 | Fleet master agreements, call-offs, consolidated billing | MS3 | 11 | 13 | 3
3.2.2 | Floor plan lines, curtailments, payoff on sale | MS3 | 12 | 14 | 3
3.2.3 | Sold-out-of-trust AI alerts, stock audits | MS3 | 13 | 14 | 2
3.3 | Risk and accounting
3.3.1 | Collections v1 and propensity models | MS3 | 11 | 13 | 3
3.3.2 | Repossession and remarketing workflows | MS3 | 12 | 14 | 3
3.3.3 | TFRS 9 ECL engine v1 | MS3 | 12 | 14 | 3
3.4 | Proof and certification
3.4.1 | Parallel run on 100k-contract book | MS3 | 13 | 14 | 2
3.4.2 | SOC 2 Type I and ISO 27001 readiness | MS3 | 10 | 14 | 5
3.4.3 | First leasing customer go-live | MS3 | 14 | 14 | 1
4 | Phase 3 · Commercial, trade, treasury
4.1 | Commercial banking
4.1.1 | Limits, collateral, covenants, group exposure | MS4 | 15 | 17 | 3
4.1.2 | Credit applications with authority matrix | MS4 | 15 | 17 | 3
4.1.3 | SME term loans, revolving credit, overdraft | MS4 | 16 | 18 | 3
4.1.4 | Cash management: sweeps, bulk payments, statements | MS4 | 17 | 19 | 3
4.2 | Retail bank extensions
4.2.1 | Branch and teller | MS4 | 16 | 18 | 3
4.2.2 | Floating-rate home loans | MS4 | 17 | 19 | 3
4.3 | Trade, treasury, syndication foundations
4.3.1 | Contingent ledger, guarantees, sight import LCs | MS4 | 16 | 19 | 4
4.3.2 | Currency positions, rates, customer FX, nostro, FTP | MS4 | 16 | 19 | 4
4.3.3 | RFR engine and syndication lender role | MS4 | 17 | 20 | 4
4.4 | Scale and accounting
4.4.1 | Multi-GAAP books, regulatory data marts | MS4 | 17 | 20 | 4
4.4.2 | Billion-account test | MS4 | 19 | 20 | 2
4.5 | Business
4.5.1 | Series B funding | MS4 | 18 | 20 | 3
4.5.2 | Commercial pilot customer live | MS4 | 20 | 20 | 1
4.5.3 | SOC 2 Type II, ISO 27001 certification | MS4 | 15 | 20 | 6
5 | Phase 4 · Scale and platform
5.1 | SaaS and global platform
5.1.1 | Tenant onboarding automation, per-tenant cells | MS5 | 21 | 24 | 4
5.1.2 | Multi-region active-active (ADR-0008) | MS5 | 23 | 30 | 8
5.1.3 | Migration factory and parallel-run tooling | MS5 | 21 | 26 | 6
5.2 | Markets
5.2.1 | Full LC lifecycle, collections, SCF, AI document checks | MS5 | 21 | 26 | 6
5.2.2 | FX and money-market deals, revaluation, LCR and NSFR, CLS | MS5 | 22 | 27 | 6
5.2.3 | Syndication agent: drawdowns, distribution, transfers | MS5 | 24 | 29 | 6
5.3 | AI and products
5.3.1 | Collections agents, product copilot GA, dynamic pricing | MS5 | 21 | 27 | 7
5.3.2 | Embedded finance and BNPL partner APIs | MS5 | 25 | 30 | 6
5.4 | Expansion
5.4.1 | Singapore and Malaysia jurisdiction packs | MS5 | 24 | 30 | 7
5.4.2 | Integrator partner programme | MS5 | 21 | 24 | 4
5.4.3 | First incumbent migration in parallel run | MS5 | 27 | 30 | 4
5.4.4 | Series C funding | MS5 | 28 | 30 | 3
6 | Phase 5 · Global bank
6.1 | Global capabilities
6.1.1 | Indonesia, Hong Kong, Middle East packs | MS6 | 31 | 38 | 8
6.1.2 | EU, UK, US jurisdiction packs | MS6 | 35 | 42 | 8
6.1.3 | Islamic banking product blocks | MS6 | 32 | 38 | 7
6.1.4 | Cross-border, cross-currency pooling | MS6 | 33 | 39 | 7
6.2 | Markets depth
6.2.1 | Digital trade: eUCP, electronic bills of lading | MS6 | 33 | 39 | 7
6.2.2 | Hedge accounting, IRRBB data | MS6 | 34 | 40 | 7
6.2.3 | Security agent, multi-currency revolving with swingline | MS6 | 36 | 41 | 6
6.3 | Certification and references
6.3.1 | Billion-account certification and region failover drills | MS6 | 31 | 36 | 6
6.3.2 | Tier-1 reference programme | MS6 | 36 | 42 | 7
6.3.3 | $70–100M ARR and unicorn-scale round | MS6 | 40 | 42 | 3
Legend
1 Phase 0 · Foundations
2 Phase 1 · Retail and virtual bank MVP
3 Phase 2 · Asset finance and leasing
4 Phase 3 · Commercial, trade, treasury
5 Phase 4 · Scale and platform
6 Phase 5 · Global bank
Note: coloured bar = activity period · columns = months · red header = milestone month · MSn = milestone the activity delivers to